## Marketing Plan Data
Marketing Plan Data
Marketing Plan Lists |  | Status Color Legend & Toggle
|  | Not Started | In Progress | Delayed | Complete | Custom 1 | Custom 2 | Custom 3 | Custom 4
|  | ON | ON | ON | ON | ON | ON | ON | ON
Task | Status | Owner | Assigned to | Anticipated Start Date | Anticipated End Date | Actual Start Date | Actual End Date | Estimated Cost | Actual Cost
Product Analysis | Not Started | John C. | John C. | 2025-07-01 | 2025-08-01 | 2025-06-28 |  | 1500 | 1250
Design Storyboards | In Progress | Mark M. | John C. | 2025-07-15 | 2025-08-15 | 2025-07-13 |  | 2000 | 1840
Review Storyboard Design | Delayed | Mark M. | John C. | 2025-08-01 | 2025-08-20 |  |  | 1450
Research Analysis Phase I | Complete | Kamil A. | Andrew L. | 2025-06-01 | 2025-07-01 | 2025-06-01 | 2025-06-28 | 3000 | 3200
Advertising Content Creation Phase I | Custom 1 | Kamil A. | Timothy S. | 2025-09-01 | 2025-09-15 |  |  | 500
Product Requirement Definitions | Custom 2 | Timothy S. | Vivian A. |  |  |  |  | 575 | 125
Prototype Development Specifications | Custom 3 | Kamil A. | Gabe F. | 2025-09-12 | 2025-09-25 |  |  | 1750
Quality Control, Progress Reports | Custom 4 | Mark M. | Kamil A. | 2025-07-01 | 2025-10-01 | 2025-07-01 |  | 925 | 250
Create Storyboards | Not Started | Mark M. | John C. | 2025-07-15 | 2025-08-15 | 2025-07-13 |  | 2000 | 1840
Review Storyboards with Graphic Artists | Delayed | Mark M. | John C. | 2025-08-01 | 2025-08-20 |  |  | 1450
Research Analysis Phase II | Complete | Kamil A. | Andrew L. | 2025-06-01 | 2025-07-01 | 2025-06-01 | 2025-06-28 | 3000 | 3200
Advertising Content Creation Phase II | Not Started | Kamil A. | Timothy S. | 2025-09-01 | 2025-09-15 |  |  | 500
Go to Marketing Plan Lists

## List Data
Marketing Plan Lists
Marketing Plan Data
Name | Title
John C. | Marketing Specialist
Mark M. | Marketing Manager
Kamil A. | Project Manager
Phil G. | Marketing Analyst
Andrew L. | Research Coordinator
Timothy S. | Marketing Specialist
Vivian A. | Marketing Analyst
Gabe F. | Associate Marketing Manager
Go to Marketing Plan Data